ChatAVG Agent Platform V2

План реализации, этапы, спринты и тестирование

Version 2.0 | 6 May 2026

Strategic decision: TypeScript Agent Runtime + MCP Provider Mesh + OpenAI MCP Server + sandbox-per-chat execution model.

# Содержание

1. Цель и рамки плана

2. Принципы delivery

3. Этапы проекта

4. Спринты

5. Testing strategy

6. Release gates

7. Риски и mitigation

8. Командные роли

9. Backlog artifacts

10. Источники

# 1. Цель и рамки плана

Цель плана - организовать полный rewrite ChatAVG под новую архитектуру: TypeScript Agent Runtime, MCP Provider Mesh, отдельный OpenAI MCP Server и модель независимых асинхронных sandbox-agents на каждый чат.

Delivery goal: Выпустить ChatAVG Agent Platform V2 без сохранения provider-монолита внутри Core и без потери ключевых возможностей: chat, RAG, sources, streaming, health, usage, admin observability.

Core: TypeScript, API Gateway, Agent Runtime, queue, state store, sandbox manager, approval manager, event bus.

OpenAI MCP Server: отдельный сервис с Responses API, Retrieval/vector stores/file search, embeddings, streaming, structured outputs.

MCP Mesh: минимум OpenAI MCP + Local Tools MCP; расширяемость под Custom RAG, Google и DeepSeek.

Sandbox: изолированный workspace для каждого чата/агента, lifecycle, artifacts, snapshots, resumable state.

Testing: unit, contract, integration, e2e, evals, security, load, chaos, migration regression.

# 2. Принципы delivery

| Принцип | Решение |
| --- | --- |
| OpenAI-first, not OpenAI-only | OpenAI MCP Server является P0, остальные провайдеры появляются как независимые MCP-серверы позже. |
| No provider SDK in Core | Core не импортирует OpenAI SDK. Только MCP client, contracts и domain types. |
| Async by default | Каждый пользовательский запрос создает AgentRun, который может стримить, ждать tool approval и возобновляться. |
| Sandbox isolation | Каждый чат имеет изолированный sandbox/workspace и scoped credentials. |
| Contract-first MCP | Сначала фиксируются tool schemas, error schemas и streaming event schemas, потом реализация. |
| Testing gates per sprint | Спринт не закрывается без unit + contract + integration smoke + обновленных runbooks. |

# 3. Этапы проекта

| Этап | Спринты | Главный результат |
| --- | --- | --- |
| Phase 0 - Architecture lock | Sprint 0 | Согласованы контракты, ADR, target architecture, migration boundary. |
| Phase 1 - Core foundation | Sprint 1-2 | TypeScript monorepo, Agent Runtime skeleton, MCP gateway/client, event bus. |
| Phase 2 - OpenAI MCP Server | Sprint 3-4 | Responses API, streaming, embeddings, vector store primitives, normalized response. |
| Phase 3 - Async sandbox agents | Sprint 5-6 | AgentSession, AgentRun queue, sandbox lifecycle, artifacts, pause/resume. |
| Phase 4 - RAG and tools | Sprint 7-8 | OpenAI managed RAG, file search, Custom RAG MCP integration, tool approvals. |
| Phase 5 - Production hardening | Sprint 9-10 | Evals, security, load tests, observability, migration, release gate. |

# 4. Спринты

## Sprint 0 - Architecture lock and baseline

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Зафиксировать ADR: MCP Provider Mesh, OpenAI MCP Server outside Core, sandbox-per-chat. - Описать existing ChatAVG behavior как regression baseline. - Утвердить доменные контракты: ChatSession, AgentSession, AgentRun, ToolCall, Artifact. - Утвердить MCP tool catalog для OpenAI MCP Server v1. | - Architecture Decision Record - Domain model draft - MCP tool contracts draft - Regression checklist | - Architecture review - Threat-model review - Baseline smoke tests старой версии |

## Sprint 1 - TypeScript monorepo and Core skeleton

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Создать TypeScript monorepo: core, shared-contracts, openai-mcp-server, local-tools-mcp-server. - Настроить lint, format, strict tsconfig, test runner, CI. - Создать API Gateway skeleton: /healthz, /api/chats, /api/agent-runs. - Добавить config/env validation. | - Working TS monorepo - Core service starts - Health endpoints - CI pipeline | - Unit tests config/env - API smoke tests - Type checks strict - Docker build smoke |

## Sprint 2 - MCP Gateway and contract-first mesh

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Реализовать MCP client abstraction в Core. - Описать registry MCP servers: openai, local-tools, custom-rag placeholder. - Сделать tool discovery, capability registry и error mapping. - Добавить fake MCP server для contract tests. | - MCP Gateway - Tool registry - Fake MCP test server - Contract test suite | - MCP schema validation - Tool discovery tests - Timeout/retry tests - Failure mapping tests |

## Sprint 3 - OpenAI MCP Server MVP

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Создать отдельный openai-mcp-server. - Реализовать tools: openai.responses.create, openai.responses.stream. - Нормализовать output_text, usage, model, latency, responseId. - Добавить store=false по умолчанию и metadata support. | - OpenAI MCP MVP - NormalizedResponse - Streaming POC - Provider health endpoint | - Unit tests response mapper - Integration tests with mocked OpenAI - Streaming contract tests - Error mapper tests |

## Sprint 4 - Embeddings and vector store primitives

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Добавить openai.embeddings.create. - Добавить vectorStores.create, files.upload, vectorStores.search. - Сделать document ingestion facade через OpenAI MCP. - Добавить source mapping: file, chunk, score, retrievalMode. | - OpenAI managed retrieval primitives - Document ingestion API - RetrievalResult schema | - Embedding contract tests - Vector store mock integration - Source mapping tests - Cost/usage estimate tests |

## Sprint 5 - Async Agent Runtime

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Создать AgentRun queue и worker. - Добавить AgentRun state machine: queued, running, tool_calling, waiting_for_approval, completed, failed, cancelled. - Реализовать event bus для streaming в UI. - Сохранение trace на каждый run. | - Async agent execution - Event stream - Run state store - Trace records | - State machine tests - Queue retry tests - Cancellation tests - Event ordering tests |

## Sprint 6 - Sandbox lifecycle

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Реализовать Sandbox Manager interface. - Добавить local/docker sandbox provider для dev. - Поддержать manifest, mounted files, artifacts, snapshots, cleanup. - Связать ChatSession -> AgentSession -> SandboxSession. | - Sandbox-per-chat MVP - Artifact extraction - Snapshot/resume POC | - Sandbox create/run/cleanup tests - Artifact tests - Isolation tests - Resume tests |

## Sprint 7 - RAG profiles and Custom RAG MCP integration

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Сделать RAG profiles: no_retrieval, openai_managed, custom_hybrid, ensemble. - Подключить Custom RAG MCP placeholder или adapter к legacy retrieval. - Реализовать citation builder на уровне Core. - Добавить answerability policy для пустого retrieval. | - RAG profile router - Citation contract - Custom RAG MCP integration path | - Retrieval routing tests - Citation accuracy tests - Empty retrieval tests - RAG eval smoke |

## Sprint 8 - Tool approvals and security control plane

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Реализовать ToolPolicy, approval requests, approval UI events. - Разделить read-only и high-risk tools. - Добавить prompt-injection checks для tool outputs. - Добавить audit log для всех MCP calls. | - Approval manager - Tool audit log - Security policy enforcement | - Approval bypass tests - Schema validation tests - Sensitive data redaction tests - Prompt injection regression tests |

## Sprint 9 - Observability, evals and load testing

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Ввести metrics: latency, queue depth, tool calls, cost, token usage, retrieval hit rate. - Собрать eval dataset: simple chat, RAG, sources, tool calls, sandbox artifacts. - Добавить load tests: concurrent chats and long-running agents. - Добавить runbooks для incidents. | - Metrics dashboard - Eval runner - Load test report - Operational runbooks | - Eval pass threshold - P95 latency tests - Queue saturation tests - Failure-rate tests |

## Sprint 10 - Migration, hardening and release

| Scope | Deliverables | Testing gate |
| --- | --- | --- |
| - Мигрировать UI на AgentRun events. - Провести regression against legacy baseline. - Отключить provider-monolith path. - Подготовить deployment, secrets, backup, rollback plan. | - Release candidate - Migration report - Rollback plan - Production checklist | - End-to-end tests - Security review - Disaster recovery drill - Release gate sign-off |

# 5. Testing strategy

Тестирование строится как обязательная часть архитектуры, потому что агентская платформа имеет больше failure modes, чем обычный request/response backend.

| Уровень тестов | Что проверяет | Инструменты / подход |
| --- | --- | --- |
| Unit | Domain types, mappers, policies, state machine, cost estimator | Vitest/Jest, strict TypeScript |
| Contract | MCP schemas, tool inputs/outputs, error contracts, streaming events | JSON Schema, fake MCP servers, snapshot tests |
| Integration | Core -> MCP Gateway -> OpenAI MCP mock, queue, state store, sandbox provider | Docker compose, mocked OpenAI, test containers |
| End-to-end | User message -> AgentRun -> MCP calls -> streaming -> final answer | Playwright/API tests, local sandbox |
| RAG evals | Answer correctness, source coverage, citation faithfulness, empty retrieval behavior | Eval dataset + automated graders + human spot review |
| Security | Approval gates, data leakage, prompt injection via tool outputs, SSRF/URL trust | Abuse tests, policy tests, red-team prompts |
| Load | Concurrent chats, long-running agents, queue backpressure, streaming fanout | k6/Artillery, synthetic workload |
| Chaos | MCP server unavailable, OpenAI timeout, sandbox crash, queue retry, partial streaming failure | Fault injection tests |

# 6. Release gates

No provider SDK imports in ChatAVG Core.

OpenAI MCP Server passes all contract tests for Responses, streaming, embeddings and vector store search.

AgentRun state machine has deterministic transitions and recovery behavior.

Sandbox isolation tests prove files, secrets and artifacts do not leak between chats.

High-risk tools cannot run without approval.

RAG answers have citations in at least 95% of answerable knowledge-base cases.

P95 latency meets target for simple chat and RAG chat under expected concurrency.

Load test proves queue backpressure instead of uncontrolled overload.

Security review signs off MCP server trust levels and data-sharing logs.

Rollback plan tested before production cutover.

# 7. Риски и mitigation

| Риск | Вероятность | Влияние | Mitigation |
| --- | --- | --- | --- |
| Rewrite scope creep | High | High | Жесткий P0/P1/P2 backlog, Sprint 0 architecture lock, no optional providers до OpenAI MCP v1. |
| Recursive OpenAI-through-MCP design | Medium | High | Правило: Core invokes OpenAI MCP; OpenAI model may call external MCP tools, not OpenAI MCP itself. |
| MCP security/data leakage | Medium | High | Approval policy, data classification, audit logs, trusted server registry, output validation. |
| Sandbox cost/latency | Medium | Medium | Sandbox pooling для trusted workloads, cleanup policy, TTL, lightweight path для simple chat. |
| Retrieval quality regression | Medium | High | RAG eval dataset, ensemble fallback, citation metrics, legacy custom RAG as MCP service. |
| Streaming complexity | Medium | Medium | Unified AgentRunEvent schema, event ordering tests, replayable event log. |
| Provider API changes | Medium | Medium | OpenAI SDK/contract isolated in OpenAI MCP Server only. |

# 8. Командные роли

| Роль | Ответственность |
| --- | --- |
| Tech Lead / Architect | ADR, domain model, architecture reviews, API boundaries, release gate. |
| Core Backend Engineer | TypeScript Core, Agent Runtime, queue, state store, event bus. |
| MCP/OpenAI Engineer | OpenAI MCP Server, Responses API, retrieval, embeddings, vector stores, streaming. |
| Sandbox Engineer | Sandbox Manager, Docker/local provider, artifacts, snapshots, isolation. |
| Security Engineer | Tool policies, approvals, threat model, MCP trust, data leakage tests. |
| QA/Evals Engineer | Test matrix, eval datasets, e2e, load, regression gates. |
| Frontend Engineer | AgentRun status UI, streaming events, approval UI, artifact UI. |
| DevOps/SRE | CI/CD, deployment, secrets, observability, rollback, incident runbooks. |

# 9. Backlog artifacts

ADR-001: ChatAVG Agent Platform V2 architecture.

ADR-002: OpenAI MCP Server outside Core.

ADR-003: Sandbox-per-chat lifecycle and isolation policy.

ADR-004: MCP Provider Mesh contracts and trust levels.

SPEC-001: AgentRun state machine.

SPEC-002: MCP tool schemas for OpenAI MCP Server.

SPEC-003: Streaming AgentRunEvent schema.

SPEC-004: Tool approval and audit log schema.

SPEC-005: RAG profiles and citation contract.

RUNBOOK-001: OpenAI MCP outage.

RUNBOOK-002: Sandbox cleanup failure.

RUNBOOK-003: High queue depth and backpressure.

EVAL-001: RAG + citations baseline.

EVAL-002: Tool-use and approval baseline.

# Источники и технологическая база

OpenAI Responses API migration guide: https://developers.openai.com/api/docs/guides/migrate-to-responses?update-multiturn=chat-completions

OpenAI Retrieval and semantic search guide: https://developers.openai.com/api/docs/guides/retrieval#semantic-search

OpenAI MCP and Connectors guide: https://developers.openai.com/api/docs/guides/tools-connectors-mcp

OpenAI Sandbox Agents guide: https://developers.openai.com/api/docs/guides/agents/sandboxes