# ChatAVG Agent Platform v2.3

## Оптимизированный delivery-план, спринты, тестирование и release gates

Версия: 2.3
Дата: 7 мая 2026
Статус: Ready for Architecture Approval / Implementation Planning
Назначение: заменить предыдущий план v2.1/v2.2 единым, более эффективным планом реализации ChatAVG Agent Platform с ранней проверкой ER Meaning Layer, production-ready runtime и управляемым rollout.

## 1. Executive summary

План v2.3 объединяет лучшее из последних документов и устраняет главный риск предыдущей дорожной карты: смысловой слой ChatAVG не должен появляться в конце проекта. Если ChatAVG позиционируется как meaning-first платформа, то SemanticProtocol, Claim Ledger, DomainBoundary и проверки языка должны быть проверены до тяжелых инвестиций в RAG, sandbox, tool mesh и enterprise hardening.

Главная корректировка v2.3: Semantic Protocol Proof-of-Concept переносится в Sprint 5. Это создает ранний product/USP gate: если система не умеет стабильно извлекать claims, понижать силу утверждений и удерживать domain boundaries, дальнейшая инфраструктура корректируется до того, как накоплен дорогой технический долг.

План сохраняет технически правильные решения последних документов:

- Fast path first: простой чат не проходит через sandbox, live tool discovery и heavy RAG.

- Model Gateway: inference отделен от MCP tools; LiteLLM Proxy используется как primary gateway-кандидат.

- Durable Agent Runtime: AgentRun реализуется через Temporal-first подход, без попытки построить полноценный workflow engine на SQLite.

- MCP Tool Gateway: MCP используется для tools/connectors, с versioned schemas и Tool Registry.

- Risk-based sandbox / Forge: E2B primary для code/browser/high-risk действий; no sandbox-per-chat default.

- Policy / Cost / Audit control plane: решения allow/deny/approval/downgrade входят в execution path.

- ER Meaning Layer: Claim Ledger, DomainBoundary, Role Passes и Artifact Workspace становятся продуктовым ядром, а не поздним украшением.

## 2. Что изменено относительно предыдущего плана

| Область | Было | Решение v2.3 | Зачем |
| --- | --- | --- | --- |
| ER Meaning Layer | Sprint 11-12 | Sprint 5 PoC + Sprint 11-12 углубление | Проверить USP рано, снизить риск поздней переделки. |
| Durable execution | SQLite outbox MVP с поздним Temporal | Temporal-first dev/staging; SQLite только app DB/audit/fallback | Не писать заново timers, saga, locks, approval waits. |
| Model layer | Existing provider factory + будущий gateway | LiteLLM pilot в Sprint 4 + compatibility adapter | Быстрее получить routing, budgeting, fallback, virtual keys. |
| Sandbox | Risk-based, но поздно | E2B primary в Sprint 14, policies уже в Sprint 8 | Не запускать sandbox на каждый чат, но подготовить control plane заранее. |
| RAG | Sprint 9-10 | Sprint 10-11 после Semantic PoC и MVP | Не строить retrieval до проверки смыслового слоя и event contracts. |
| Testing | Поздние evals | Semantic eval seed в Sprint 5, full evals Sprint 11 | Качество становится delivery gate, а не финальным отчетом. |
| Delivery | Линейный план | С Sprint 5 параллельные tracks | Инфраструктура и meaning/product track двигаются одновременно. |

## 3. Интеграция источников

| Источник | Что взято | Что изменено / отвергнуто |
| --- | --- | --- |
| Google Doc “Анализ и оптимизация ChatAVG v2” | Shift-left ER-layer, ранний Semantic Protocol PoC, параллельные tracks, отказ от самописного SQLite workflow engine, high-stakes positioning. | Sprint 4.5 преобразован в Sprint 5 для нормального sprint accounting. |
| v2.2 Detailed Backlog / ADR / Risk Register | Temporal primary, LiteLLM primary, E2B primary + Daytona alternative, risk register, detailed backlog artifacts. | Temporal переносится раньше; SQLite не считается полноценным DurableRuntime. |
| “Архитектурная реализация ChatAVG v2.0” | Meaning-first, Mission Lifecycle, Adequacy Engine, Role Passes, Artifact Workspace, semantic observability. | ER-layer становится P0/P1, не late-stage layer. |
| “Concept v2 / Architecture Review” | Fast path, provider-neutral core, Model/Knowledge/MCP Tool Gateways, latency budgets, cost/audit plane, migration/rollout. | OpenAI-first сохраняется как provider choice, но не как core semantics. |
| Старый Implementation Plan | Contract-first delivery, testing gates, runbooks, eval/load/chaos levels. | Отвергнуты big-bang rewrite, default sandbox-per-chat и “MCP для всего inference”. |
| Текущий репозиторий ChatAVG | Existing Node.js/Express gateway, SQLite, provider adapters, policyRouter/fallbackPolicy, MCP gateway, tests, UI audit. | План — evolutionary migration, не переписывание “с нуля”. |

## 4. Non-negotiable architecture decisions

- Simple chat stays simple: no sandbox, live tool discovery or heavy retrieval in fast path.

- MCP is for tools, not model inference by default: inference идет через ModelGateway.

- Core is provider-neutral: provider-specific logic lives behind gateways/adapters.

- Durability is a platform property: AgentRun survives restart, approval wait, retries, cancellation, provider failure.

- No custom workflow engine trap: SQLite is not a replacement for Temporal signals/timers/replay.

- Semantic layer shifts left: Claim Ledger and DomainBoundary are tested before RAG/sandbox expansion.

- Risk-based sandboxing: full sandbox only for code/browser/write/high-risk.

- Policy/cost/audit are in the execution path: not post-fact telemetry.

- Human sovereignty: value/trajectory choices return to the human through ConflictCard/DecisionRecord.

- No hidden authority: the system must not speak stronger than the evidence allows.

## 5. Delivery model

### 5.1. Tracks after Sprint 5

| Track | Фокус | Основные спринты | Owner |
| --- | --- | --- | --- |
| Track A — Platform Infrastructure | ModelGateway, AgentRun, Temporal, Policy, Sandbox, ToolGateway | 4, 6, 7, 8, 13, 14, 15 | Tech Lead / Backend Lead |
| Track B — Meaning/Product | SemanticProtocol, ClaimLedger, RolePasses, ArtifactWorkspace, Mission Room UX | 5, 9, 11, 12 | Product + Semantic Lead |
| Track C — Knowledge Quality | KnowledgeGateway, RAG modes, RAG evals, citation correctness | 10, 11, 15 | ML / Evals Lead |
| Track D — QA/Security/Ops | Test harness, security gates, load/chaos, release runbooks | 1, 8, 11, 15, 16 | QA/Security/SRE |
| Track E — Frontend/UX | AgentRun events, approvals, Mission Room, Artifact diffs, mobile UI | 6, 8, 9, 12, 16 | Frontend / UX Lead |

### 5.2. Critical path

Sprint 0 → Sprint 1 → Sprint 2 → Sprint 3 → Sprint 4
          → Sprint 5 Semantic PoC Gate
          → Sprint 6 AgentRun
          → Sprint 7 Temporal
          → Sprint 8 Policy/Approval
          → Sprint 9 MVP Gate
          → Sprint 10-14 Product/Tools/Forge expansion
          → Sprint 15 Hardening
          → Sprint 16 Release Candidate

### 5.3. MVP and release logic

- MVP Gate: Sprint 9. MVP must show fast chat, AgentRun, Semantic PoC, policy/approval and traceable artifact draft.

- Beta Gate: after Sprints 12-14. Beta must show KnowledgeGateway, RolePasses, ArtifactWorkspace, ToolGateway and Forge path.

- Release Candidate: Sprint 16. RC requires full regression, evals, security review, load/chaos, rollback dry-run and V1 fallback.

## 6. Roadmap overview

| Sprint | Название | Главный результат | Gate |
| --- | --- | --- | --- |
| 0 | Repo hygiene and architecture lock | Чистый repo, ADR pack, feature flags, baseline | Architecture lock |
| 1 | Regression baseline | Надежные tests + fixtures + latency/security baseline | Test harness gate |
| 2 | Fast path discipline | CanonicalChatEvent + simple chat guardrails | Fast path gate |
| 3 | Model Registry | Dynamic models list + provider health/admin | Registry gate |
| 4 | Model Gateway + LiteLLM pilot | Gateway boundary + cost/routing/fallback pilot | Gateway gate |
| 5 | Semantic Protocol PoC | Claim/Boundary PoC + semantic eval seed | USP viability gate |
| 6 | Mission + AgentRun API | AgentRun state/event stream + Mission context | Runtime API gate |
| 7 | Temporal DurableRuntime | Durable workflows, approval signals, replay | Durability gate |
| 8 | Policy/Cost/Audit/Approval | Control plane in execution path | Safety gate |
| 9 | MVP Release | Fast chat + AgentRun + Semantic PoC + approvals | MVP gate |
| 10 | Knowledge Gateway | RAG modes + Citation contract | RAG architecture gate |
| 11 | RAG + Semantic Evals | Quality thresholds and nightly evals | Quality gate |
| 12 | Role Passes + Artifact Workspace | Traceable artifacts and Mission Room UX | Meaning product gate |
| 13 | MCP Tool Gateway | Versioned tool contracts and registry | Tool contract gate |
| 14 | Hybrid Sandbox / Forge | E2B sandbox for high-risk execution | Forge safety gate |
| 15 | Observability + load/chaos | Performance, reliability, cost dashboards | Hardening gate |
| 16 | Release Candidate | Migration, rollback, security sign-off | RC gate |

## 7. Detailed sprint plan

### Sprint 0 — Repo hygiene, architecture lock and planning reset

Длительность: 1 неделя
Цель: Очистить репозиторий, зафиксировать v2.3 и убрать конфликтующие направления.

Scope / задачи:

- Закрыть или переписать PR #1; не мержить нерелевантную console utility и сломанный .gitignore.

- Восстановить .gitignore: *.gguf, models_cache/, runtime data, secrets, env-файлы, временные артефакты.

- Обновить PROJECT_BACKLOG.md: новая линия — fast path + AgentRun + Temporal + risk-based Forge.

- Принять ADR pack: fast path, ModelGateway/LiteLLM, Temporal, E2B/Daytona, MCP Tool Gateway, Semantic shift-left.

- Зафиксировать feature flags: agent_runs_enabled, model_gateway_enabled, litellm_enabled, semantic_layer_enabled, knowledge_gateway_enabled, tool_gateway_enabled, sandbox_forge_enabled, temporal_runtime_enabled.

- Составить current baseline: endpoints, tests, adapters, DB schema, UI gaps, latency baseline.

Deliverables:

- ADR pack v2.3

- Обновленный PROJECT_BACKLOG.md

- Baseline checklist

- Decision record по PR #1

- Release branch strategy

Testing Gate:

- cd cons/chatavg && npm test

- Smoke: login → sessions → chat completion with mocked provider

- Manual UI smoke: desktop + mobile 375px

- node dev_studio/refresh.js обновляет PROJECT_MAP.md

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 1 — Regression baseline and test harness hardening

Длительность: 2 недели
Цель: Сделать тесты надежным сигналом перед изменением runtime/gateways/semantic-layer.

Scope / задачи:

- Разделить тесты на unit/integration/security/contract/smoke.

- Изолировать test DB: отдельный каталог, deterministic seed, cleanup, fixtures.

- Починить CORS/SSRF/JSON-limit/prompt-sanitization assertions.

- Добавить synthetic provider для детерминированных latency/streaming тестов.

- Снять baseline P50/P95/P99 для simple chat, fallback, session load/save.

- Собрать CI matrix: PR, nightly, release.

Deliverables:

- Test Matrix v1

- Fixtures pack

- Synthetic provider

- Baseline latency/security report

- CI command plan

Testing Gate:

- Unit config/utils/repositories

- Integration auth/session/admin/chat

- Security CORS/SSRF/payload/prompt tests

- UI smoke no console errors

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 2 — Canonical contracts and fast path discipline

Длительность: 2 недели
Цель: Защитить simple chat fast path и стабилизировать CanonicalChatEvent.

Scope / задачи:

- Опубликовать SPEC-001 CanonicalChatEvent: delta/done/error/tool_call/retrieval/usage/trace.

- Покрыть adapters contract tests на AsyncIterable semantics.

- Запретить sandbox/live tool discovery/heavy retrieval в simple path.

- Ввести latency budgets: auth/routing, context load, provider TTFT, total latency.

- Сохранить backward compatibility /api/chat/completions.

- Добавить guardrail test: heavy dependencies in fast path = failure.

Deliverables:

- SPEC-001 CanonicalChatEvent

- Fast Path Contract

- Provider adapter contract tests

- Latency budget dashboard draft

Testing Gate:

- Streaming event ordering

- Non-streaming mapper

- Retryable fallback only

- Synthetic latency smoke

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 3 — Model Registry and provider administration

Длительность: 2 недели
Цель: Закрыть pending Model Registry и подготовить Model Gateway без SDK leakage.

Scope / задачи:

- Реализовать production-grade ai.models.list: cache TTL, partial failure, provider timeout, metadata.

- Добавить ModelRegistry: modelId/providerId/capabilities/cost class/health/fallback eligibility.

- Сделать admin endpoint для models list/provider health.

- Синхронизировать UI status-dot с health contract.

- Описать policy видимости моделей по категориям.

- Подготовить migration note для category settings.

Deliverables:

- SPEC-002 ModelRegistry

- Admin models endpoint

- Provider health/status contract

- UI health update plan

Testing Gate:

- Mocked ai.models.list

- Cache hit/miss/expiry

- Provider unavailable → partial result

- UI status regression

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 4 — Model Gateway boundary with LiteLLM pilot

Длительность: 2 недели
Цель: Выделить inference/routing в ModelGateway и запустить LiteLLM как primary gateway-кандидат.

Scope / задачи:

- Опубликовать SPEC-003 ModelGateway: request/stream/normalized response/usage/latency/error mapping.

- Сделать thin adapter поверх existing provider factory для backward compatibility.

- Запустить LiteLLM Proxy в dev/staging: virtual keys, routing, fallback, cost tracking.

- Добавить trace events model.requested, model.stream_started, model.completed, model.failed, cost.committed.

- Развести терминологию: ModelGateway ≠ MCP ToolGateway.

- Подготовить cost mapping: modelId → token price/cost class → budget policy.

Deliverables:

- SPEC-003 ModelGateway

- LiteLLM dev integration

- Model trace mapper

- Cost mapping v0

- Compatibility report

Testing Gate:

- Model request/response contract

- Streaming via ModelGateway

- Timeout/fallback/error mapper

- Cost event assertions

- Backward compatibility tests

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 5 — Semantic Protocol Proof-of-Concept — shift-left USP validation

Длительность: 2 недели
Цель: Рано доказать, что ER Meaning Layer работает до RAG/sandbox/tool-mesh инвестиций.

Scope / задачи:

- Принять ADR-005 Semantic shift-left.

- Создать SemanticProtocol v0: glossaryVersion, strength levels, domain boundary rules, no-hidden-authority rules.

- Реализовать Claim extraction pipeline: claim type, source span, strength, level, uncertainty.

- Реализовать DomainBoundary detector and strength downgrade.

- Создать seed dataset 50-100 кейсов: legal/compliance, consulting, scientific, ambiguous, adversarial.

- Добавить semantic eval runner: claim accuracy, boundary violation, no psychodiagnosis, no hidden authority.

- Сделать UX concept: показывать 3-5 главных различений, не всю механику.

Deliverables:

- SPEC-004 SemanticProtocol v0

- SPEC-005 Claim/DomainBoundary v0

- EVAL-001 Semantic seed set

- Semantic PoC report

- UX sketch

Testing Gate:

- Semantic golden tests

- Boundary downgrade tests

- No hidden authority regression

- No psychodiagnosis regression

- Manual review 20 cases

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 6 — Mission and AgentRun API foundation

Длительность: 2 недели
Цель: Ввести AgentRun и Mission как execution единицы, привязанные к SemanticProtocol.

Scope / задачи:

- Опубликовать SPEC-006 AgentRun state machine: queued/running/requires_action/waiting/completed/failed/cancelled/expired.

- Добавить Mission: missionId, semanticProtocolId, glossaryVersion, mode, goal, constraints, open questions.

- Добавить endpoints: create run, status, cancel, event stream.

- Добавить AgentRunEvent: run/model/retrieval/tool/approval/semantic/artifact/cost events.

- Сделать bridge: simple chat fast path, complex/mission tasks through AgentRun.

- Не смешивать SessionRepository с execution history.

Deliverables:

- SPEC-006 AgentRun

- SPEC-007 Mission model

- SSE event stream MVP

- AgentRun API MVP

- Semantic context attached to run

Testing Gate:

- State transition tests

- Event ordering

- Cancel/reconnect

- No duplicate run

- Semantic context persistence

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 7 — Durable Runtime — Temporal-first implementation

Длительность: 2-3 недели
Цель: Внедрить Temporal рано, не строя полноценный workflow engine на SQLite.

Scope / задачи:

- Опубликовать SPEC-008 DurableRuntime: start/signal/cancel/wait/checkpoint/replay/query.

- Запустить Temporal dev cluster и worker для AgentRun workflows.

- Реализовать workflow: model step, semantic step, wait-for-approval timer, cancellation, retry with idempotency.

- Оставить SQLite для app DB/audit/lightweight dev fallback, не для timers/sagas/locks.

- Добавить payload policy: small events in Temporal, large artifacts external storage.

- Написать RUNBOOK-001 restart/replay/recovery.

Deliverables:

- SPEC-008 DurableRuntime

- Temporal worker MVP

- AgentRun workflow v0

- RUNBOOK-001

- Temporal/local fallback decision

Testing Gate:

- Worker restart/replay

- Approval signal

- Cancellation

- Timer/timeout

- Idempotency

- Temporal unavailable degradation

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 8 — Policy, cost, audit and approval primitives

Длительность: 2 недели
Цель: Сделать control plane частью execution path до большого расширения tools/sandbox.

Scope / задачи:

- Опубликовать SPEC-009 PolicyEngine: allow/deny/require_approval/require_step_up_auth/downgrade.

- Опубликовать SPEC-010 CostPolicy and AgentRunEstimate.

- Расширить AuditService v2: model/retrieval/tool/approval/sandbox/semantic/cost events.

- Добавить ApprovalRequest states: pending/approved/rejected/edited/timeout/expired.

- Ввести risk score 0-100 and riskClass.

- Добавить redaction: secrets/sensitive payloads не попадают в prompts или model-visible traces.

Deliverables:

- SPEC-009 PolicyEngine

- SPEC-010 CostPolicy

- SPEC-011 ApprovalRequest

- Audit schema v2

- Risk scoring matrix

Testing Gate:

- Policy unit tests

- Cost estimate tests

- Approval states

- Audit assertions

- Redaction/security tests

- Approval bypass tests

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 9 — MVP release gate — Fast chat + AgentRun + Semantic PoC + Policy/Approval

Длительность: 2 недели
Цель: Собрать первый MVP, демонстрирующий инфраструктуру и смысловую ценность.

Scope / задачи:

- Собрать E2E: login → fast chat → mission → AgentRun → semantic claim extraction → approval pause → artifact draft.

- Включить feature flags для internal beta users.

- Сделать MVP dashboard: run status, latency, cost, semantic events, approval events.

- Провести product review ER-layer usefulness.

- Провести security review MVP.

- Подготовить MIGRATION-001: V1 fallback and rollback to fast path.

Deliverables:

- MVP release notes

- MIGRATION-001

- Internal beta checklist

- MVP quality report

- Known limitations list

Testing Gate:

- Full MVP E2E

- Auth/session/chat/admin regression

- Security abuse tests

- Semantic eval smoke

- Manual desktop/mobile UI

- Rollback dry-run

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 10 — Knowledge Gateway and RAG modes

Длительность: 2 недели
Цель: Вывести retrieval в mode-driven KnowledgeGateway.

Scope / задачи:

- Опубликовать SPEC-012 KnowledgeGateway: no_retrieval/fast/balanced/max_quality.

- Реализовать router: query classification → mode → retriever → citation validation.

- Сохранить legacy/custom retrieval as adapter path, not ChatService logic.

- Подключить cost/trace events к RAG generation.

- Добавить answerability policy для empty retrieval.

- Добавить RetrievalResult and Citation contract: sourceId, chunkId, score, provenance, boundary notes.

Deliverables:

- SPEC-012 KnowledgeGateway

- SPEC-013 RetrievalResult/Citation

- RAG mode router

- Answerability policy

Testing Gate:

- Retrieval routing

- Citation schema validation

- Empty retrieval

- Latency per mode

- RAG smoke

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 11 — RAG evals, semantic evals and quality thresholds

Длительность: 2 недели
Цель: Перевести качество RAG и ER-layer в измеряемые gates.

Scope / задачи:

- Создать EVAL-002 RAG dataset: answerable/unanswerable/citation-required/multi-source/adversarial.

- Интегрировать RAGAS/TruLens-compatible metrics где уместно.

- Расширить semantic evals: claim accuracy, boundary, strength downgrade, no hidden authority.

- Добавить nightly eval pipeline: small PR smoke + full nightly + release full.

- Определить quality gates по режимам.

- Сделать human spot review protocol.

Deliverables:

- EVAL-002 RAG dataset

- EVAL-003 Semantic expanded dataset

- Eval runner

- Quality dashboard spec

- Human review protocol

Testing Gate:

- CI eval smoke

- Nightly full eval

- Manual review sample

- Regression threshold tests

- Adversarial prompt suite

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 12 — Role Passes, Artifact Workspace and Mission Room UX

Длительность: 2-3 недели
Цель: Связать ER Meaning Layer с видимыми артефактами и рабочим UX.

Scope / задачи:

- Опубликовать SPEC-014 RolePass: Observer/Boundary/Language/System/Trajectory/Builder.

- Ввести Adequacy Covenant: не превышать область определения, не смешивать уровни, не говорить от имени непроверяемого.

- Реализовать ArtifactWorkspace: Artifact/ArtifactPatch/version/source claims/decision records/export state.

- Сделать patch/diff viewer.

- Реализовать Mission Room MVP: goal, context, open questions, 3-5 distinctions, conflict cards.

- Скрыть debug-механику, показывать смысловые итоги.

Deliverables:

- SPEC-014 RolePass

- SPEC-015 ArtifactWorkspace

- Mission Room MVP

- Artifact patch viewer

- ConflictCard/DecisionRecord v0

Testing Gate:

- Role contract tests

- Artifact versioning/diff

- Patch references claim/decision

- Semantic UX smoke

- No hidden authority regression

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 13 — MCP Tool Gateway and versioned Tool Registry

Длительность: 2 недели
Цель: Подключать tools/connectors через безопасный, версионированный MCP boundary.

Scope / задачи:

- Опубликовать SPEC-016 MCP Tool Gateway: protocol/transport/auth/schema versioning/timeout/retry/error semantics.

- Реализовать Tool Registry cache: providerId + toolName + toolVersion + schemaHash.

- Ввести ToolDefinitionVersion: schemas/riskClass/authScope/approvalPolicyId/timeoutMs/retryPolicyId.

- Разделить risk classes: read/write/external_side_effect/code_exec/browser/privileged.

- Добавить ToolCall state machine.

- Требовать idempotencyKey для side-effect tools.

Deliverables:

- SPEC-016 MCP Tool Gateway

- Tool Registry MVP

- ToolCall state machine

- Fake MCP tool server

- Canary tool rollout guide

Testing Gate:

- JSON schema contracts

- Tool timeout/retry

- Error mapping

- Idempotency required

- Canary version

- Secrets redaction

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 14 — Hybrid Sandbox / Forge with E2B primary

Длительность: 3 недели
Цель: Материализовать code/browser/write/high-risk actions без sandbox-per-chat default.

Scope / задачи:

- Опубликовать SPEC-017 SandboxManager: assign/run/snapshot/freeze/terminate/cleanup/quarantine.

- Интегрировать E2B primary; Daytona/local as dev/alternative.

- Реализовать execution classes: low-risk text/retrieval/read/write/code/browser/privileged.

- Full sandbox только для code/browser/write/high-risk.

- Реализовать workspace mount, artifact extraction, TTL, idle timeout, cleanup, snapshots.

- Добавить egress policy: default deny, tenant allowlist, provider endpoints, signed URLs.

- Добавить quarantine for suspicious artifacts.

Deliverables:

- SPEC-017 SandboxManager

- E2B integration MVP

- Forge v0

- Egress policy

- RUNBOOK-002 sandbox cleanup/quarantine

Testing Gate:

- Sandbox create/run/cleanup

- Isolation tests

- Egress deny/allow

- Artifact extraction/quarantine

- Sandbox crash recovery

- Cost/TTL enforcement

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 15 — Observability, load, chaos, multi-provider fallback and operational hardening

Длительность: 3 недели
Цель: Доказать надежность, стоимость, observability и graceful degradation.

Scope / задачи:

- Собрать dashboards: cost, P95 latency, approvals, sandbox warm/cold, RAG quality, semantic quality.

- Ввести Trace Bus as source of truth; external tools only overlay.

- Load tests: fast chats, RAG chats, AgentRun streams, long workflows, tools, sandbox.

- Chaos tests: provider timeout, LiteLLM unavailable, Temporal restart, vector store unavailable, MCP down, sandbox crash.

- Multi-provider fallback pilot.

- Backpressure вместо uncontrolled provider overload.

Deliverables:

- Observability dashboards

- Load test report

- Chaos report

- RUNBOOK-003 backpressure

- RUNBOOK-004 provider outage

- Fallback report

Testing Gate:

- Load harness

- Chaos fault injection

- Recovery/replay

- Fallback model tests

- Dashboard event completeness

- DR drill

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

### Sprint 16 — Release Candidate, migration, security review and controlled rollout

Длительность: 2 недели
Цель: Закрыть architecture/security/performance/semantic/migration gates перед production rollout.

Scope / задачи:

- Full regression against V1 baseline.

- Security review: prompt injection, tool escalation, cross-tenant leakage, egress, secrets, approval bypass.

- Full eval: RAG, semantic, role passes, artifacts, tool approvals, refusal/recovery.

- Подготовить MIGRATION-002: feature flags, shadow, canary, rollback.

- Подготовить runbooks для Temporal/LiteLLM/E2B/Knowledge/ToolGateway/cost spike.

- Rollback dry-run and backup/restore drill.

- Release sign-off: Architecture, Backend, Frontend, QA/Evals, Security, DevOps, Product.

Deliverables:

- Release candidate report

- MIGRATION-002

- Security sign-off

- Full eval report

- Production checklist

- Post-release backlog

Testing Gate:

- Full E2E

- Security red-team suite

- Load/chaos release gate

- Backup/restore/rollback drill

- Manual visual UI gate

Exit Criteria: все deliverables приняты, testing gate прошел, PROJECT_MAP.md и PROJECT_BACKLOG.md обновлены, изменения закрыты за feature flags или documented migration boundary.

## 8. Testing strategy

Тестирование является частью архитектуры, а не финальной стадией. Агентская платформа имеет больше failure modes, чем request/response backend: provider timeouts, partial streams, workflow replay, approval waits, tool side effects, sandbox crashes, retrieval hallucinations and semantic overreach.

### 8.1. Test levels

| Уровень | Что проверяет | Где запускать | Blocking policy |
| --- | --- | --- | --- |
| Unit | Domain types, mappers, policies, state machines, cost estimator, semantic rules | PR | Блокирует PR |
| Contract | CanonicalChatEvent, ModelGateway, AgentRunEvent, ToolDefinitionVersion, MCP schemas | PR | Блокирует PR |
| Integration | Core → ModelGateway, Core → Temporal worker, DB, audit/cost events, KnowledgeGateway mock | PR / staging | Блокирует merge в release branch |
| E2E | login → session → fast chat → AgentRun → approval → artifact | PR smoke + release full | Блокирует release |
| Security | CORS, SSRF, prompt injection, tool output injection, approval bypass, secrets leakage, egress | PR smoke + release full | Zero critical allowed |
| RAG evals | answerability, context precision/recall, citation correctness, hallucination, latency/cost | nightly + release | Блокирует release по threshold |
| Semantic evals | Claim extraction, DomainBoundary, strength downgrade, no hidden authority, no psychodiagnosis | PR smoke + nightly | Блокирует MVP/RC gates |
| Load | concurrent chats, event-stream fanout, queue/backpressure, sandbox allocation | staging/release | Блокирует RC |
| Chaos | provider timeout, Temporal worker restart, vector store unavailable, MCP down, sandbox crash | staging/release | Блокирует RC |
| Visual/UI | desktop, mobile 375px, approval UI, Mission Room, artifact diff | sprint closure | Блокирует sprint closure |

### 8.2. CI pipeline

PR pipeline:
  npm run lint
  npm run test:unit
  npm run test:contract
  npm run test:security:smoke
  npm run test:integration:smoke
  npm run eval:semantic:smoke

Nightly pipeline:
  npm run test:integration:full
  npm run eval:rag:full
  npm run eval:semantic:full
  npm run test:security:abuse
  npm run test:load:small

Release pipeline:
  full regression
  full RAG eval
  full Semantic eval
  full E2E browser suite
  load + chaos
  rollback dry-run
  security sign-off

### 8.3. Quality thresholds for release gates

| Area | MVP target | RC target |
| --- | --- | --- |
| Fast path TTFT P95 on synthetic provider | no regression vs baseline | no regression vs baseline |
| Simple chat no sandbox/tool/RAG guardrail | 100% | 100% |
| AgentRun duplicate creation on reconnect | 0 | 0 |
| Approval bypass for high-risk actions | 0 | 0 |
| Claim extraction accuracy on golden set | ≥ 80-85% | ≥ 90% |
| DomainBoundary violation detection | ≥ 80% | ≥ 90% |
| No hidden authority critical violations | 0 | 0 |
| RAG citation correctness | smoke only | ≥ 90-95% after corpus calibration |
| Side-effect tool idempotency coverage | 100% for enabled tools | 100% |
| Sandbox isolation leakage | 0 | 0 |
| Cost event coverage for model/tool/sandbox | ≥ 95% | ≥ 99% |
| Rollback dry-run | documented | executed successfully |

## 9. Release gates

| Gate | Название | Exit criteria |
| --- | --- | --- |
| A | Architecture Lock | ADR pack accepted, old sandbox-per-chat default removed, feature flags ready, V1 fallback documented. |
| B | Fast Path Safety | Simple chat route protected, backward compatibility proven, fallback does not bypass policy. |
| C | Semantic Viability | Claim/DomainBoundary PoC passes golden set, no hidden authority, product usefulness confirmed. |
| D | MVP | Fast chat + AgentRun + Semantic PoC + Policy/Approval works end-to-end with rollback. |
| E | Beta | KnowledgeGateway, RolePasses, ArtifactWorkspace, ToolGateway and Forge v0 pass gates. |
| F | Release Candidate | Security, evals, load/chaos, rollback dry-run and runbooks signed off. |

## 10. Risk register

| Risk | Вероятность | Влияние | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Late USP risk: ER-layer проверяется слишком поздно | Высокая | Критическое | Sprint 5 Semantic PoC gate | Product + Semantic Lead |
| Команда застрянет на самописном SQLite workflow engine | Средняя | Высокое | Temporal-first Sprint 7, SQLite only app DB/audit/fallback | Tech Lead |
| LiteLLM интеграция задержит ModelGateway | Средняя | Среднее | Thin compatibility adapter first, LiteLLM feature flag | Backend Lead |
| Fast path замедлится из-за AgentRun/Temporal overhead | Средняя | Высокое | Guardrail tests: no sandbox/RAG/tool discovery in simple path | Performance Lead |
| Semantic evals требуют много ручной разметки | Высокая | Среднее | Seed dataset early, LLM-as-judge + human spot review | Evals Lead |
| Approval fatigue | Высокая | Высокое | Grouped approvals, edit-then-approve, smart defaults | UX Lead |
| RAG quality ниже ожиданий | Средняя | Высокое | RAGAS/TruLens metrics, nightly evals, no ensemble default | ML/Evals Lead |
| Tool schema drift | Средняя | Среднее | schemaHash, canary rollout, contract tests | Backend Lead |
| Prompt injection через tool output | Высокая | Высокое | Output validation, redaction, policy checks, adversarial tests | Security Lead |
| Sandbox cost explosion | Высокая | Среднее | Risk-based sandbox, TTL, budgets, warm-pool metrics | DevOps Lead |
| Cross-tenant leakage | Низкая | Критическое | Isolation tests, scoped credentials, audit review | Security Lead |
| Temporal operational complexity | Средняя | Среднее | Dev cluster early, runbooks, team training, fallback mode | SRE Lead |
| Model provider outage | Средняя | Высокое | ModelGateway fallback, second provider pilot Sprint 15 | Backend/SRE |
| UI exposes too much internal machinery | Средняя | Среднее | “3-5 distinctions” UX rule, usability review | UX Lead |
| Meaning layer becomes mystical/overconfident | Средняя | Критическое | No hidden authority evals, Adequacy Covenant, Language Pass | Semantic Lead |
| Release rollback fails | Низкая | Критическое | MIGRATION-002 + rollback dry-run before RC | DevOps Lead |

## 11. Backlog artifacts

### ADRs

- ADR-001: Fast path + evolutionary migration boundary.

- ADR-002: ModelGateway with LiteLLM primary and provider-neutral core.

- ADR-003: DurableRuntime with Temporal primary.

- ADR-004: Risk-based sandbox / E2B primary + Daytona alternative.

- ADR-005: Semantic shift-left and ER Meaning Layer viability gate.

- ADR-006: MCP ToolGateway scope and versioned Tool Registry.

- ADR-007: KnowledgeGateway modes and no ensemble default.

- ADR-008: Policy/Cost/Audit as execution control plane.

### SPECs

- SPEC-001: CanonicalChatEvent.

- SPEC-002: ModelRegistry.

- SPEC-003: ModelGateway.

- SPEC-004: SemanticProtocol.

- SPEC-005: ClaimLedger and DomainBoundary.

- SPEC-006: AgentRun state machine.

- SPEC-007: Mission model.

- SPEC-008: DurableRuntime interface.

- SPEC-009: PolicyEngine.

- SPEC-010: CostPolicy and AgentRunEstimate.

- SPEC-011: ApprovalRequest.

- SPEC-012: KnowledgeGateway.

- SPEC-013: RetrievalResult and Citation.

- SPEC-014: RolePass contract.

- SPEC-015: ArtifactWorkspace.

- SPEC-016: MCP ToolGateway and ToolDefinitionVersion.

- SPEC-017: SandboxManager and Forge.

### EVALs

- EVAL-001: Semantic seed set.

- EVAL-002: RAG answerability/citations dataset.

- EVAL-003: Semantic adversarial set.

- EVAL-004: Tool approval and bypass dataset.

- EVAL-005: Artifact traceability dataset.

- EVAL-006: Recovery/refusal/degradation dataset.

### RUNBOOKs and migrations

- RUNBOOK-001: Temporal restart/replay/recovery.

- RUNBOOK-002: Sandbox cleanup/quarantine failure.

- RUNBOOK-003: High queue depth/backpressure.

- RUNBOOK-004: Model provider outage / LiteLLM unavailable.

- RUNBOOK-005: KnowledgeGateway/vector store unavailable.

- RUNBOOK-006: Cost spike / quota exceeded.

- RUNBOOK-007: Security incident: tool escalation or data leakage.

- MIGRATION-001: MVP rollout with V1 fallback.

- MIGRATION-002: Production rollout and rollback.

- MIGRATION-003: Data migration for Mission/AgentRun/Semantic traces.

- MIGRATION-004: Provider configuration migration to ModelRegistry/ModelGateway.

## 12. Definition of Done

### Sprint DoD

Every sprint closes only when:

- Scope is merged behind feature flags where appropriate.

- Unit/contract/integration tests for affected area pass.

- Security smoke tests pass for changed boundaries.

- Manual UI smoke is done on desktop and 375px mobile.

- PROJECT_MAP.md is updated with node dev_studio/refresh.js.

- PROJECT_BACKLOG.md is updated with completed items, files touched and date.

- Any new public/internal contract has SPEC or ADR update.

- No new direct provider SDK leakage into Core without ADR.

- No hidden authority or unsafe depth handling introduced by semantic changes.

### Architecture DoD

- AgentRuntime, ModelGateway, KnowledgeGateway, MCP ToolGateway, SandboxManager and PolicyEngine are separated.

- AgentRun supports retry/resume/cancel/approval wait without duplicated side effects.

- Simple chat remains fast path and does not allocate sandbox.

- All side-effect ToolCalls have idempotencyKey.

- Model/cost/audit events are emitted consistently.

### Meaning-first DoD

- Every strong claim has type, level, strength and domain boundary.

- The system can downgrade claims when evidence is insufficient.

- Role passes produce bounded patches, not theatrical debate.

- ConflictCards return value/trajectory choices to the human.

- Artifacts contain traceable decisions and open boundaries.

### Security/Cost DoD

- High-risk actions require approval and audit.

- Sandbox egress is default-deny.

- Secrets are scoped and never model-visible.

- Budget policies can stop, downgrade or request approval.

- Cost per successful chat is a top-level dashboard metric.

## 13. Migration and rollout

### Rollout controls

- Feature flags by tenant, workspace, user and agent profile.

- V1 fallback for critical tenants and high-risk workflows.

- Shadow mode for ModelGateway routing and RAG answers before production use.

- A/B comparison on latency, cost, success rate, approval conversion, semantic quality and retention.

- Canary rollout for ToolDefinitionVersion and provider changes.

- Rollback procedure tested before production enablement.

### Migration phases

| Phase | Scope | Exit criteria |
| --- | --- | --- |
| Phase 0 | Repo hygiene, tests, fast path, ModelGateway pilot | No regression vs V1 baseline |
| Phase 1 | Semantic PoC + AgentRun + Temporal + policy | MVP gate passed |
| Phase 2 | KnowledgeGateway + evals + Role/Artifact UX | Beta gate passed |
| Phase 3 | MCP ToolGateway + Forge/Sandbox | Tool/Forge gates passed |
| Phase 4 | Observability + load/chaos + multi-provider fallback | RC gate passed |
| Phase 5 | Tenant-by-tenant production rollout | Rollback ready, owner matrix active |

## 14. Team roles and ownership

| Role | Responsibilities |
| --- | --- |
| Tech Lead / Architect | ADRs, boundaries, critical reviews, release gate authority. |
| Backend Lead | ModelGateway, AgentRun API, PolicyEngine, ToolGateway contracts. |
| Runtime Engineer | Temporal workflows, worker lifecycle, replay/recovery. |
| Semantic Lead | SemanticProtocol, ClaimLedger, DomainBoundary, RolePass contracts. |
| ML/Evals Engineer | RAG evals, semantic evals, regression thresholds, human review protocol. |
| Frontend/UX Lead | AgentRun status, approvals, Mission Room, Artifact diffs, mobile UX. |
| Security Engineer | Threat model, approval bypass, prompt/tool injection, sandbox egress, secrets. |
| DevOps/SRE | CI/CD, Temporal/LiteLLM/E2B deployment, observability, rollback, runbooks. |
| Product Manager | Scope control, MVP/beta criteria, user feedback, prioritization. |

## 15. Immediate next actions

- Update PROJECT_BACKLOG.md to v2.3 and mark old sandbox-per-chat default as superseded.

- Close or rewrite PR #1; restore .gitignore protections before any feature work.

- Create ADR-005 Semantic shift-left and make Sprint 5 a formal product/architecture gate.

- Create docs/specs/SPEC-001-canonical-chat-event.md and docs/specs/SPEC-004-semantic-protocol.md.

- Split tests into stable commands and introduce synthetic provider.

- Create first 50 semantic golden cases before building advanced RAG.

- Start LiteLLM dev proxy only behind feature flag.

- Start Temporal dev cluster before implementing custom workflow logic.

- Define MVP demo script for Sprint 9 now, not during Sprint 9.

- Add a release gate dashboard skeleton early: latency, cost, failures, approvals, semantic quality.

## 16. Final planning formula

ChatAVG v2.3 delivery =
  Repo discipline
  + reliable tests
  + protected fast path
  + ModelGateway/LiteLLM
  + early SemanticProtocol PoC
  + AgentRun/Temporal
  + Policy/Cost/Audit/Approval
  + KnowledgeGateway/Evals
  + RolePasses/ArtifactWorkspace
  + MCP ToolGateway
  + risk-based Forge/E2B
  + load/chaos/security rollout gates

Главный критерий успеха: ChatAVG не должен стать просто еще одной агентской платформой. Он должен доказать, что умеет работать с силой утверждений, границами применимости, человеческими развилками и traceable artifacts лучше, чем обычный чат или обычный tool-calling framework.